PROFAB PROJECT LIFECYCLE JF Requirements Traceability & Verification L1 clarity • L2 process control • L3 forms & matrices CONTROLLED REVIEW COPY 30 August 2026 ¦ Version 1.0 Prepared for ProFab / JF management review

01 / EXECUTIVE ASSURANCE

# Lifecycle implemented and verified

Outcome The application now implements the source-definable JF lifecycle as a connected three-layer operating model: a simple 13-node L1, a 14-node L2 with a distinct G1 and bounded commercial route, and an L3 containing all 52 controlled form records, two matrices, eight Gate/final controls, and enforceable completion logic.

| 13 L1 lifecycle nodes | 14 L2 process nodes | 52 L3 controlled forms | 79 functional & UI checks |
| --- | --- | --- | --- |

## What is complete

Exact Initial Contact → Final Close high-level lifecycle with five primary Gates.

Evidence → Rules → Eligibility → Route → Score qualification logic; no score can override a hard rule.

All 52 indexed/supplemental documents represented as operational L3 records, each with a 10-field controlled schema.

Approval Matrix: 52 forms + 5 Gates = 57 rows across six approval-role columns.

Responsibility Matrix: 18 whole-project delivery areas across four core-party columns.

Completion, signature, approval, task, applicability and N/A controls tested for bypass resistance.

Production build, console/network health, responsive layouts and accessible control naming verified.

## Important qualification

No policy was invented The provided Master Requirements explicitly leaves several legal, payment, signing and release decisions as TBD. The system exposes working control points but does not silently convert those open decisions into final company policy. Section 9 lists every retained TBD.

## Report map

| Section | Contents |
| --- | --- |
| 1 | Executive assurance |
| 2 | Evidence basis & source integrity |
| 3 | Three-layer lifecycle architecture |
| 4 | JF requirement traceability |
| 5 | Complete L3 form & matrix register |
| 6 | Gate 1 enforcement design |
| 7 | Scenario and regression verification |
| 8 | Bug & UI review |
| 9 | Retained management decisions (TBD) |
| 10 | Acceptance conclusion |

02 / EVIDENCE BASIS

# Source integrity and interpretation rules

Quotation basis The left-hand wording in the traceability table is quoted verbatim from JF_Master_Requirements_All_Conversations_2026-08-29.docx. That file describes itself as a compiled Master Requirements summary, not a word-for-word conversation transcript. Accordingly, this report labels the text as source wording from the Master summary—not as a direct transcript quote.

| Evidence source | Use in this review | Observed condition |
| --- | --- | --- |
| JF_Master_Requirements_All_Conversations_2026-08-29.docx | Requirements, working directions and explicit TBDs | 12 rendered pages; internally coherent summary |
| Combined Forms.pdf | Controlled index, included form bodies, revisions and numbering | 193 pages; forms usable through page 178; pages 179–193 corrupted binary render |
| Current PROFAB Project Lifecycle application | Existing architecture, implementation target and verification surface | Production build and browser flows tested locally |

## Controlled-form reconciliation

| 52 digital L3 records | 21 included templates | 30 index-only templates | 1 supplemental template |
| --- | --- | --- | --- |

The nine-page PDF register contains 51 indexed entries.

SMO 2.13.1 exists on PDF pages 114–116 but is omitted from that index; it is preserved as the 52nd supplemental controlled record.

The 21 Included records use the source form pages/revisions as evidence; 30 Index Only records receive a controlled operational digital schema without pretending that a missing PDF body was supplied.

PDF pages 179–193 render embedded XLSX/DOCX binary data and are not treated as forms.

DC/CD and SOW/PSO/WMA numbering conflicts are exposed to users rather than silently normalized away.

Figure 1. L3 source-package QA visible inside the live Approval Matrix.

03 / THREE-LAYER ARCHITECTURE

# L1 is simple; L2 explains; L3 executes

Layer contract L1 answers ‘where is the project?’ L2 answers ‘what process and Gate comes next?’ L3 answers ‘what evidence, form, matrix, signature, approval or task makes that status true?’

## L1 — exact high-level lifecycle

Figure 2. The complete 13-node L1 lifecycle and five primary Gates.

| # | Type | L1 node | Linked L2 node(s) |
| --- | --- | --- | --- |
| 1 | Start | INITIAL CONTACT | Project Start |
| 2 | Phase | OPPORTUNITY & QUALIFICATION | Opportunity & Qualification |
| 3 | Primary Gate | G1 — QUALIFIED & COMMERCIALLY ENGAGED | G1 — Qualified & Commercially Engaged |
| 4 | Phase | PRE-CONSTRUCTION | Commercial Pathway + Pre-Construction |
| 5 | Primary Gate | G2 — PROJECT / TECHNICAL COMMITMENT | G2 — Project / Technical Commitment |
| 6 | Phase | PRODUCTION READINESS | Production Readiness |
| 7 | Primary Gate | G3 — PRODUCTION AUTHORIZATION | G3 — Production Authorization |
| 8 | Phase | FACTORY PRODUCTION | Factory Production |
| 9 | Primary Gate | G4 — FACTORY COMPLETION / RELEASE | G4 — Factory Completion / Release |
| 10 | Phase | DELIVERY / PROJECT COMPLETION | Delivery / Project Completion |
| 11 | Primary Gate | G5 — PROJECT COMPLETION / WARRANTY START | G5 — Project Completion / Warranty Start |
| 12 | Phase | COMMISSIONING & WARRANTY | Commissioning & Warranty |
| 13 | End | FINAL CLOSE | Final Close |

Figure 3. L1 phase cards show explicit links into their L2 process nodes.

03 / THREE-LAYER ARCHITECTURE

# L2 — bounded process with independent Gates

| L2 node | Purpose | L1 parent |
| --- | --- | --- |
| Project Start | Entry record and project identifier | L1 Initial Contact |
| Opportunity & Qualification | Six-step Gate 1 evidence and routing workspace | L1 Opportunity |
| G1 — Qualified & Commercially Engaged | Independent release point; no bypass | L1 G1 |
| Commercial Pathway | Bounded CSA → Class D → PCS, governed LOI modifier | L1 Pre-Construction |
| Pre-Construction | Design, site, estimating, scope and responsibilities | L1 Pre-Construction |
| G2 — Project / Technical Commitment | Class C basis and project/technical commitment | L1 G2 |
| Production Readiness | Drawings, PSO, materials, permit, payment, schedule and changes | L1 Production Readiness |
| G3 — Production Authorization | Controlled factory release | L1 G3 |
| Factory Production | Production, QC, inspection and rework | L1 Factory Production |
| G4 — Factory Completion / Release | Completion evidence plus transport/site readiness | L1 G4 |
| Delivery / Project Completion | Site, delivery, set, interfaces, deficiencies | L1 Delivery |
| G5 — Project Completion / Warranty Start | Acceptance, deficiency disposition and warranty basis | L1 G5 |
| Commissioning & Warranty | Startup, handover, claims and expiry tracking | L1 Commissioning & Warranty |
| Final Close | Commercial and obligation reconciliation | L1 Final Close |

Figure 4. Opportunity cannot bypass G1; the controlled commercial pathway begins only after release.

03 / THREE-LAYER ARCHITECTURE

# L3 — controlled evidence, not a document dump

Every catalog form opens inside the L3 execution layer with a controlled identity, revision, language, applicability decision, lifecycle links, source reference and ten operational fields. Form values are not enough on their own: required signature, approval, task and status controls must also pass.

| Control | Effective behavior |
| --- | --- |
| Applicability | Required is always applicable; Conditional/Triggered begin Pending; Optional/Supporting do not gate by default. |
| Required data | All required form fields must contain objective values before Complete/Passed becomes selectable. |
| N/A | Not Applicable requires an objective reason; blank or whitespace evidence remains incomplete. |
| Signature | Signed is mandatory where configured; Partially Signed is not complete; Rejected is blocked. |
| Approval | Approved is mandatory where configured; Rejected is blocked. |
| Protection | Catalog forms and Gate controls cannot be deleted; Clear L3 only removes custom items. |
| Roll-up | Only effective L3 progress counts in the L2 status summary. |

Figure 5. A live CEC form shows revision, language, lifecycle links, required fields and blocking status.

04 / REQUIREMENT TRACEABILITY

# JF source wording → implemented node/control

The left column preserves the Master Requirements summary wording. The right column identifies the corresponding live node/control and its verification evidence.

| JF source wording (verbatim from Master Requirements summary) | Implemented node(s), control and evidence |
| --- | --- |
| §3 · Master summary | Implemented System architecture: L1 defines the whole lifecycle; L2 defines process and Gates; L3 owns forms, signatures, approvals and versions. Evidence: Figs. 1–4. |
| §3 · Master summary | Implemented L1 contains exactly five primary Gates. Technical, commercial, payment, design and release conditions stay in L2/L3. Evidence: Figs. 1–3. |
| §3 · Master summary | Implemented Five Gate nodes are independent L2 release points. Forms supply evidence but no form is used as the Gate itself. |
| §3 · Master summary | Implemented Commercial Pathway limits early routing to CSA, Class D, PCS, governed LOI, Hold or No-Go; direct Opportunity → Commercial bypass is removed. Evidence: Fig. 3. |
| §3 · Master summary | Implemented Gate 1 collects named authority, role, approval path, scale, site, design, budget, funding and team evidence. Missing authority evidence is a hard Hold. Evidence: Fig. 5. |
| §3 · Master summary | Implemented L1/L2 include site, delivery, commissioning, warranty and Final Close; the 18-row Responsibility Matrix tracks civil/foundation/site interfaces. |
| §3 · Master summary | Implemented Progressive L1 → L2 → L3 disclosure; status summaries roll from L3 to L2. Gate 1 explains route, Hold reason, risks and next action. |
| §3 · Master summary | Implemented Every catalog form has a locked index/code/title, controlled revision and language. Matrix/source QA exposes discrepancies. Evidence: Figs. 4 and 6. |
| §3 · Master summary | Implemented 63 rule tests, 9 interaction tests and 7 responsive/accessibility tests exercise hard stops, route abuse, form bypasses and UI regressions. |
| §4 · Master summary | Implemented L1 is the exact 13-node Initial Contact → Final Close view with five highlighted primary Gates. Evidence: Figs. 1–2. |
| §4 · Master summary | Implemented Only G1–G5 are primary Gates. PDAF, SA, PSO, payment and procurement controls remain linked L3 records/conditions. |
| §5 · Master summary | Implemented Each Gate has release conditions, an approval execution item, responsible authority and GO/HOLD status aggregation. |
| §5 · Master summary | Implemented Each form has lifecycle touchpoints; CEC, SOW, RM, changes, incidents and warranty records link across multiple L2 stages. |
| §6 · Master summary | Implemented Opportunity & Qualification implements six ordered steps: evidence, hard blockers, plan qualification, route, LOI governance, Gate dossier. Score cannot release a hard stop. |
| §6 · Master summary | Implemented G1 handoff requires identity, full authority evidence, storeys + GFA, site, design and assigned/executed eligible route; other facts remain visible as actions/risks. |
| §6.1 · Master summary | Implemented Storeys and GFA are mandatory positive values for G1/Class D readiness; either missing value blocks. Module count remains optional. |
| §6.1 · Master summary | Implemented Design maturity and modular compatibility are separate fields/rules. Permit/IFC without modular review requires Technical Review and blocks G1. |
| §6.1 · Master summary | Implemented Funding In Process, Not Secured and Unknown produce visible risk flags and actions; none independently produces No-Go. |
| §6.2 · Master summary | Implemented The rule engine follows this exact order. Eligibility and route are deterministic; score is calculated last and never overrides a Hard rule. |
| §6.2 · Master summary | Implemented All four examples are encoded and tested: authority Hold; No Design → CSA; funding risk; permit-incompatible → Hold/No-Go. |
| §6.3 · Master summary | Implemented Candidate/Multiple/Unassigned/No Site routes to bounded CSA; plan routes to Class D; recorded Class D routes to PCS; governed LOI cannot shortcut the sequence. |
| §6.3 · Master summary | Implemented LOI is unavailable to Standard relationships unless policy enables it; it requires Class D evidence, scope/time caps, conversion trigger, review date and executive sign-off. |
| §7 · Master summary | Implemented Gate 1 records route readiness only and does not require or invent a Class D amount. The controlled CEC form records the later estimate basis and disclaimer evidence. |
| §7 · Master summary | Implemented Missing or non-positive storeys/GFA blocks qualification. No synthetic estimate or default $/sq.ft. amount is generated. |
| §8 · Master summary | Implemented Commercial Pathway converges early variants into the Pre-Construction/CEC stream; G2 accepts a common Class C-ready technical/scope basis. |
| §9 · Master summary | Implemented Opportunity can be re-evaluated at any step; status/rules are derived from saved evidence. L3 recurring/triggered controls preserve loops and exceptions without spaghetti. |
| §10 · Master summary | Implemented PSO is a required signed/approved L3 control linked to Production Readiness and G3; final funds/approver policy remains a documented TBD. |
| §11 · Master summary | Implemented Production Readiness aggregates drawings, PSO, materials, permit, payment, MPS and changes; G3 is a separate approval release. |
| §11 · Master summary | Implemented G4 separates Factory Completion from Release. MSO, QC, inspection, transport and site-readiness evidence remain prerequisites. |
| §12 · Master summary | Implemented G5 records warranty start; Commissioning & Warranty tracks WMA/support/notices; Final Close reconciles open obligations and acceptance. |
| §13.2 · Master summary | Implemented All 52 forms carry one home node plus one-or-more lifecycle touchpoints and one of six applicability classes; Conditional/Triggered records require an explicit decision. |
| §14 · Master summary | Implemented The L3 Responsibility Matrix stays at 18 high-level delivery areas/4 core parties; SOW is a separate detailed controlled form for exact boundaries. |
| §19 · Master summary | Implemented L1 is intentionally concise; L2 adds process/gates; L3 exposes forms, matrices, fields, approvals and evidence. Responsive behavior was verified at five widths. |
| §21 · Master summary | Implemented Complete 52-record L3 catalog, source QA, revision/language/signature/approval controls, plus automated replay scenarios and full UI tests. |

05 / L3 CONTROLLED REGISTER

# Every form has an operational schema

The digital form is intentionally more than a file link. Each of the 52 records has six common evidence fields plus four fields selected by its operational profile. If an Optional or Supporting form is used, its required internal fields still apply; its optionality only prevents it from becoming an automatic Gate prerequisite.

| Schema | Controlled fields |
| --- | --- |
| All profiles | Project name; Project/file number; Prepared by; Record date; form-specific primary record; Evidence/attachment references |
| Presentation | Intended audience; Purpose/call to action; Content revision; Release status |
| Agreement | Counterparty; Scope/commercial basis; Effective date; Execution state |
| Meeting | Meeting date; Attendees/organizations; Decisions; Open actions/owners/dates |
| Analysis | Analysis/estimate basis; Assumptions/exclusions; Findings; Recommendation/next action |
| Approval | Approval subject/revision; Authorized approver; Approval date; Decision |
| Register | Record/issue reference; Action owner; Target/response date; Record status |
| Report | Module/area/subject; Inspection/event date; Findings/evidence; Disposition |
| Instructions | Applicable revision; Prerequisites; Controlled sequence; Issued to/acknowledged by |
| Schedule | Baseline date; Period/milestone range; Critical constraints; Schedule status |
| Service | Service request; Owner; Response date; Service status |
| Package | Contents/index; Revision/change basis; Transmittal; Acceptance status |
| Notice | Recipient/authority; Event date; Impact; Response deadline |

Applicability distribution: Conditional 18, Optional 2, Required 17, Supporting 4, Triggered 11.

05 / L3 CONTROLLED REGISTER

# Complete 52-form register

| Index / code | Controlled title & operational focus | L2 home | Lifecycle touchpoints | Applicability / controls | Source / owner / approvers |
| --- | --- | --- | --- | --- | --- |
| 1.1 — | Corporate Presentation Focus: Capabilities and project evidence presented | Opportunity & Qualification | Opportunity | Supporting · Document 10 fields | Index Only Owner: Sales / Marketing Approvers: Sales, Management |
| 1.2 EOI | Expression of Interest Focus: Client interest and intended next step | Opportunity & Qualification | Opportunity → G1 | Optional · Document 10 fields | Index Only Owner: Sales Approvers: Sales |
| 2.1 CSA | Consultation Services Agreement Focus: Consultation deliverables and boundaries | Commercial Pathway | Commercial → Pre-Con | Conditional · Agreement 10 fields · signature | Included pp. 10–17 S2.1 v250528 Owner: Technical / Sales Approvers: Sales, Technical, Client |
| 2.1.1 — | Meeting #1 Focus: Initial goals, requirements, and expectations | Commercial Pathway | Commercial → Pre-Con | Conditional · Evidence 10 fields | Index Only Owner: Technical / Sales Approvers: Technical |
| 2.1.2 — | Meeting #2 Focus: Progress reviewed and scope refinements | Commercial Pathway | Commercial → Pre-Con | Conditional · Evidence 10 fields | Index Only Owner: Technical / Sales Approvers: Technical |
| 2.2 NDA | Non-Disclosure Agreement Focus: Protected information and permitted disclosure | Commercial Pathway | Commercial → Pre-Con | Conditional · Agreement 10 fields · signature | Index Only Owner: Management / Legal Approvers: Management, Client |
| 2.3 LOI | Letter of Intent Focus: Intent, limits, conversion trigger, and exclusions | Commercial Pathway | Commercial → Pre-Con | Conditional · Agreement 10 fields · signature · approval | Included pp. 18–21 S2.3 v250604 Owner: Sales / Management Approvers: Management, Client |
| 2.4 FS | Feasibility Study Focus: Feasibility question and decision boundary | Commercial Pathway | Commercial → Pre-Con → G2 | Conditional · Document 10 fields | Included pp. 22–27 S2.4 v250604 Owner: Technical Approvers: Technical, Management |
| 2.5 SA | Sales Agreement Focus: Contract scope, price basis, and key conditions | Commercial Pathway | Commercial → G2 → Prod. Ready | Conditional · Agreement 10 fields · signature · approval | Included pp. 28–53 S2.5 v250624 Owner: Sales / Management Approvers: Management, Client |
| 2.6 EDAT | Electronic Document Authorization & Transfer Focus: Authorized electronic document set and transfer method | Commercial Pathway | Commercial → Pre-Con → Prod. Ready | Conditional · Approval 10 fields · approval | Included pp. 54–56 S2.6 v250409 Owner: Document Control Approvers: Technical, Client |
| 2.7 PCS | Pre-Construction Services Focus: Authorized services, deliverables, fee basis, and limits | Commercial Pathway | Commercial → Pre-Con → G2 | Conditional · Agreement 10 fields · signature · approval | Included pp. 57–66 S2.7 v250626 Owner: Technical / Project Management Approvers: Technical, Management, Client |
| 2.8 PDAF | Preliminary Design Approval Form Focus: Design package, revision, assumptions, and exceptions | Pre-Construction | Pre-Con → G2 | Conditional · Approval 10 fields · signature · approval | Included pp. 67–69 S2.8 v250409 Owner: Technical / Client Approvers: Technical, Client |
| 2.9 SDR | Site Discovery Report Focus: Site observations, measurements, and constraints | Pre-Construction | Pre-Con → G2 → Delivery | Conditional · Evidence 10 fields | Index Only Owner: Technical / Site Approvers: Technical |
| 2.10 CEC | Cost Estimate Classification: D, C, B, A Focus: Estimate class, amount, scope basis, and maturity | Pre-Construction | Commercial → Pre-Con → G2 → Prod. Ready | Required · Document 10 fields · approval | Included pp. 70–103 S2.10 v250528 Owner: Estimating / Technical Approvers: Technical, Management |
| 2.11 RFI | Request for Information Focus: Question, drawing/specification reference, and impact | Pre-Construction | Pre-Con → Prod. Ready → Factory → Delivery | Triggered · Task 10 fields | Included pp. 104–105 S2.11 v250409 Owner: Project Management / Technical Approvers: Technical |
| 2.12 SER | Specification Exception Report Focus: Specification exception, reason, and affected scope | Pre-Construction | Pre-Con → Prod. Ready → Factory | Triggered · Evidence 10 fields · approval | Included pp. 106–108 S2.12 v250409 Owner: Technical / Quality Approvers: Technical, Client |
| 2.13 SOW | Scope of Work Focus: Scope boundaries, interfaces, inclusions, and exclusions | Pre-Construction | Pre-Con → G2 → Prod. Ready → Delivery | Required · Document 10 fields · approval | Included pp. 109–113 S2.12 v250626 QA: The included form header is numbered S2.12 while the controlled index assigns 2.13. Owner: Project Management / Technical Approvers: Technical, Management, Client |
| 2.13.1 SMO | Scope & Modular Responsibility Overview Focus: Delivery model, responsibility transfer, and interfaces | Pre-Construction | Pre-Con → G2 → Delivery | Supporting · Document 10 fields | Supplemental pp. 114–116 S2.13.1 v260629 QA: Present in the source package but omitted from the nine-page controlled index. Owner: Technical / Project Management Approvers: Technical, Management |
| 2.14 RM | Responsibility Matrix Focus: Core parties, scope lines, and unassigned interfaces | Pre-Construction | Pre-Con → G2 → Prod. Ready → Delivery → Warranty | Required · Document 10 fields · approval | Included pp. 117–149 S2.14 v250716 Owner: Project Management Approvers: Technical, Management, Client |
| 2.15 PSO | Product Signoff Form Focus: Products/materials, selections, substitutions, and revision | Production Readiness | Pre-Con → Prod. Ready → G3 | Required · Approval 10 fields · signature · approval | Included pp. 150–151 S2.2 v250409 QA: The included form header is numbered S2.2 while the controlled index assigns 2.15. Owner: Technical / Client Approvers: Technical, Management, Client |
| 2.16 PS | Project Summary Focus: Project goals, success criteria, and current baseline | Pre-Construction | Pre-Con → Prod. Ready → Delivery → Final Close | Supporting · Document 10 fields | Included pp. 152–154 S2.16 v250409 Owner: Project Management Approvers: Management |
| 2.17 CD | Change Directive Focus: Directed change, reason, affected scope, and interim authority | Production Readiness | Pre-Con → Prod. Ready → Factory → Delivery | Triggered · Approval 10 fields · signature · approval | Included pp. 155–157 S2.17 v250416 QA: The controlled index shows code DC; the included form header uses CD. CD is retained as the actual form code and the discrepancy is exposed. Owner: Project Management Approvers: Management, Client |
| 2.18 CO | Change Order Focus: Change description, price, schedule, and contract impact | Production Readiness | Pre-Con → Prod. Ready → Factory → Delivery → Final Close | Triggered · Agreement 10 fields · signature · approval | Included pp. 158–161 S2.18 v250416 Owner: Project Management / Commercial Approvers: Management, Client |
| 2.18.1 CT | CD and CO Tracker Focus: Change reference, type, scope, cost, and schedule impact | Production Readiness | Pre-Con → Prod. Ready → Factory → Delivery → Final Close | Triggered · Task 10 fields | Included pp. 162 S2.18.1 v250409 Owner: Project Management / Process Coordinator Approvers: Management |
| 2.19 ODN | Occupancy Delay Notification Focus: Delay cause, responsibility, evidence, and required cure | Delivery / Project Completion | Pre-Con → Prod. Ready → Delivery | Triggered · Evidence 10 fields · approval | Included pp. 163–164 S2.19 v250416 Owner: Project Management / Commercial Approvers: Management, Client |
| 3.1 MPS | Module Production Schedule Focus: Module sequence, release dates, and production constraints | Production Readiness | Prod. Ready → G3 → Factory → G4 | Required · Document 10 fields · approval | Index Only Owner: Factory Planning Approvers: Factory, Project Management |
| 3.2 MQC | Module Quality Control Focus: Quality checkpoint, acceptance criteria, and evidence | Factory Production | Factory → G4 | Required · Evidence 10 fields · approval | Index Only Owner: Factory Quality Approvers: Factory, Quality |
| 3.3 MIR | Module Inspection Report Focus: Module ID, inspection scope, deficiencies, and evidence | Factory Production | Factory → G4 | Required · Evidence 10 fields · approval | Index Only Owner: Factory Quality Approvers: Factory, Quality |
| 3.4 TRR | Transport Readiness Report Focus: Module IDs, route, permits, protection, and release constraints | Factory Production | Factory → G4 → Delivery | Required · Evidence 10 fields · approval | Index Only Owner: Logistics / Factory Approvers: Factory, Project Management |
| 3.5 MSO | Module Sign-Off Focus: Module ID, inspection references, open punch items, and release decision | G4 — Factory Completion / Release | Factory → G4 → Delivery | Required · Approval 10 fields · signature · approval | Included pp. 165–167 S3.5 v250409 Owner: Factory / Quality Approvers: Factory, Technical, Client |
| 4.1 SSP | Site Safety Plan Focus: Site hazards, controls, access, and emergency arrangements | Delivery / Project Completion | G4 → Delivery | Conditional · Document 10 fields · approval | Index Only Owner: General Contractor / Site Safety Approvers: Site, Management |
| 4.2 MDR | Module Delivery and Receipt Form Focus: Module IDs, carrier, delivery time, and received condition | Delivery / Project Completion | G4 → Delivery | Required · Evidence 10 fields · signature · approval | Index Only Owner: Site / Logistics Approvers: Site, Project Management |
| 4.3 MAI | Module Assembly Instruction Focus: Module type, assembly limits, interfaces, and hold points | Delivery / Project Completion | G4 → Delivery | Supporting · Document 10 fields | Index Only Owner: Technical / Site Approvers: Technical |
| 4.4 MIC | Module Installation Checklist Focus: Module ID, installation sequence, hold points, and incomplete work | Delivery / Project Completion | Delivery → G5 | Conditional · Evidence 10 fields · approval | Index Only Owner: Site / Technical Approvers: Site, Technical |
| 4.5 MSI | Module Site Inspection Report Focus: Module/site area, inspection criteria, deficiencies, and photos | Delivery / Project Completion | Delivery → G5 | Required · Evidence 10 fields · approval | Index Only Owner: Technical / Site Quality Approvers: Technical, Site |
| 4.6 MALR | Module Alignment & Leveling Report Focus: Module grid, survey readings, tolerances, and corrections | Delivery / Project Completion | Delivery → G5 | Conditional · Evidence 10 fields · approval | Index Only Owner: Site / Survey / Technical Approvers: Technical, Site |
| 4.7 WSVR | Weatherproofing & Seal Verification Report Focus: Joints/areas inspected, test method, leakage, and corrective work | Delivery / Project Completion | Delivery → G5 → Warranty | Conditional · Evidence 10 fields · approval | Index Only Owner: Envelope / Site Quality Approvers: Technical, Site |
| 4.8 UCV | Utility Connection Verification Focus: Utility system, test result, authority, and outstanding work | Delivery / Project Completion | Delivery → G5 → Warranty | Conditional · Evidence 10 fields · approval | Index Only Owner: MEP / Site Approvers: Technical, Site, Consultants |
| 4.9 MDAR | Module Damage Assessment Report Focus: Module ID, damage location, cause, severity, and photos | Delivery / Project Completion | G4 → Delivery → Warranty | Triggered · Evidence 10 fields · approval | Included pp. 168–172 S4.9 v250409 Owner: Site / Quality / Logistics Approvers: Technical, Management |
| 4.10 IRF | Incident Report Form Focus: Incident facts, location, persons, evidence, and immediate action | Delivery / Project Completion | Factory → Delivery → Warranty | Triggered · Evidence 10 fields · approval | Index Only Owner: Site Safety / Project Management Approvers: Site, Management |
| 4.10.1 IRL | Incident Response Log Focus: Incident reference, response entry, evidence, and closure criterion | Delivery / Project Completion | Factory → Delivery → Warranty → Final Close | Triggered · Task 10 fields | Index Only Owner: Project Management / Safety Approvers: Management |
| 5.1 DDSS | Delegated Design Service Statement Focus: Delegated discipline, party, scope, deliverable, and seal requirement | Commissioning & Warranty | Pre-Con → Prod. Ready → Delivery → Warranty | Conditional · Document 10 fields · approval | Index Only Owner: Technical / Consultants Approvers: Technical, Consultants |
| 5.2 MISS | Module Installation Support Service Focus: Installation issue, requested support, urgency, and boundaries | Commissioning & Warranty | Delivery → Warranty | Conditional · Task 10 fields | Index Only Owner: Technical Service Approvers: Technical, Project Management |
| 5.3 DPLR | Deficiency & Punch List Report Focus: Deficiency, location, responsibility, evidence, and acceptance criterion | Delivery / Project Completion | Delivery → G5 → Warranty → Final Close | Required · Task 10 fields · approval | Index Only Owner: Project Management / Site Quality Approvers: Technical, Client |
| 5.4 FIR | Final Inspection Report Focus: Inspection scope, authority, accepted work, and residual deficiencies | Commissioning & Warranty | Delivery → G5 → Warranty | Required · Evidence 10 fields · approval | Index Only Owner: Technical / Site Quality Approvers: Technical, Client, Consultants |
| 5.5 WMA | Warranty & Maintenance Agreement Focus: Warranty start, coverage, exclusions, maintenance, and claim route | Commissioning & Warranty | G5 → Warranty → Final Close | Required · Agreement 10 fields · signature · approval | Included pp. 173–178 S2.5 v250409 QA: The included form header is numbered S2.5 while the controlled index assigns 5.5. Owner: Warranty / Management Approvers: Management, Client |
| 5.6 PCR | Project Closeout Report Focus: Completion basis, lessons learned, and final unresolved obligations | Final Close | Warranty → Final Close | Required · Document 10 fields · approval | Index Only Owner: Project Management Approvers: Management, Client |
| 5.7 ABDP | As-Built Documentation Package Focus: As-built disciplines, revision status, deviations, and completeness | Commissioning & Warranty | Delivery → Warranty → Final Close | Required · Document 10 fields · approval | Index Only Owner: Document Control / Technical Approvers: Technical, Client, Consultants |
| 5.8 CSHF | Client Satisfaction & Handover Form Focus: Handover package, training, satisfaction, and reservations | Commissioning & Warranty | G5 → Warranty → Final Close | Required · Approval 10 fields · signature · approval | Index Only Owner: Project Management / Client Approvers: Management, Client |
| 5.9 PMRF | Photography & Media Release Form Focus: Media assets, permitted uses, restrictions, and expiry | Final Close | Warranty → Final Close | Optional · Approval 10 fields · signature · approval | Index Only Owner: Marketing / Client Approvers: Management, Client |
| 5.10 NOC | Notice of Concern Focus: Concern, facts, contract reference, requested remedy, and urgency | Final Close | Pre-Con → Factory → Delivery → Warranty → Final Close | Triggered · Task 10 fields | Index Only Owner: Client / Project Management Approvers: Client |
| 5.11 RNOC | Response to Notice of Concern Focus: NOC reference, response position, corrective plan, and closure evidence | Final Close | Pre-Con → Factory → Delivery → Warranty → Final Close | Triggered · Task 10 fields · approval | Index Only Owner: Project Management / Management Approvers: Management, Client |

05 / L3 MATRICES & RELEASE CONTROLS

# Matrices connect documents to accountable roles

| Matrix | Size | Columns | Purpose |
| --- | --- | --- | --- |
| Approval Matrix — Forms & Actions | 57 rows | Sales; Technical; Project Mgmt; Factory/Site; Management; Client/Consultants | 52 controlled forms + G1–G5 |
| RM — Responsibility Matrix | 18 rows | GC/Builder; ProFab/Guildcrest; Client/Owner; Consultants | Whole-project responsibilities from authority/design through warranty/final close |

## Eight non-form L3 controls

Gate 1 objective evidence dossier

Gate 1 commercial engagement confirmation

G1 qualified & commercially engaged approval

G2 project / technical commitment approval

G3 production authorization

G4 factory completion / release approval

G5 project completion / warranty start approval

Final close commercial and obligation reconciliation

06 / GATE 1 CLIENT ENFORCEMENT

# Evidence—not score—stops non-compliant clients

| Gate 1 step | Release logic |
| --- | --- |
| 1. Objective Intake | Client, relationship, authority status, storeys, GFA, site and design basis are recorded. |
| 2. Hard Blockers | Authority, full decision group, named role evidence, approval path, scale, fatal site and modular incompatibility are enforced. |
| 3. Plan Qualification | No design → CSA; Plan + scale → Class D; no amount is invented. |
| 4. Commercial Routing | Assigned route must be one of the currently eligible bounded routes. |
| 5. LOI Governance | When used: eligible relationship/policy, named executive, bounded scope/days/hours, review date and paid conversion trigger. |
| 6. G1 Handoff | All prior checks plus an Executed commercial instrument; dossier records rules, route, score, risks and open actions. |

Hard-rule precedence: The score is a management quality indicator only. A 100/100 opportunity remains Hold, Blocked or No-Go whenever a hard rule is active.

Figure 6. Confirmed authority cannot pass without a named role and documented approval path; Eligibility Cleared remains disabled.

07 / VERIFICATION

# Representative enforcement scenario matrix

The table below lists 48 representative qualification and form-bypass paths. The automated rule suite contains 63 checks; browser interaction and UI suites add 16 further checks.

| ID | Scenario | Expected enforcement | Verified result |
| --- | --- | --- | --- |
| Q01 | Valid confirmed authority + Plan + scale | Class D route; G1 may pass without a pre-G1 estimate amount | PASS — Class D; G1 passes |
| Q02 | No Design | Route to paid CSA; never automatic No-Go | PASS — CSA; G1 can pass |
| Q03 | Decision authority Unknown | Hard Hold regardless of score | PASS — HOLD |
| Q04 | Decision authority Partially Confirmed | Hard Hold; cannot be treated as final | PASS — HOLD |
| Q05 | Final authority explicitly No | Hard Hold | PASS — HOLD |
| Q06 | Authority marked Confirmed; name/role blank | Objective-evidence Hold | PASS — HOLD |
| Q07 | Decision parties Yes; approval path blank | Approval-path Hold | PASS — HOLD |
| Q08 | Required decision parties No/Unknown | Hard Hold | PASS — HOLD |
| Q09 | Storeys and GFA both missing | Block; no fake Class D | PASS — BLOCKED |
| Q10 | Storeys missing; GFA present | Block incomplete scale | PASS — BLOCKED |
| Q11 | GFA missing; storeys present | Block incomplete scale | PASS — BLOCKED |
| Q12 | Candidate Site | Bounded CSA route + site risk | PASS — CSA |
| Q13 | Multiple Sites | Bounded CSA route + site risk | PASS — CSA |
| Q14 | Municipal land not assigned | Bounded CSA route + site risk | PASS — CSA |
| Q15 | No Site | Bounded CSA/site-feasibility route | PASS — CSA |
| Q16 | Fatal site/logistics issue, not resolvable | No-Go; archive route | PASS — NO-GO |
| Q17 | Fatal issue potentially resolvable | Hold pending approved resolution | PASS — HOLD |
| Q18 | Permit Issued + Not Compatible + no corrective path | No-Go; maturity cannot override compatibility | PASS — NO-GO |
| Q19 | Permit Issued + Not Reviewed | Technical Review required; G1 blocked | PASS — TECH REVIEW |
| Q20 | IFC/Construction Ready + Not Reviewed | Technical Review required; G1 blocked | PASS — TECH REVIEW |
| Q21 | Partially Compatible | Technical Review required | PASS — TECH REVIEW |
| Q22 | Major Rework Likely | Technical Review required | PASS — TECH REVIEW |
| Q23 | Not Compatible + corrective path Unknown | Hold for technical decision | PASS — HOLD |
| Q24 | Funding In Process | Risk only; not automatic No-Go | PASS — risk visible |
| Q25 | Funding Not Secured | Distinct risk; no false ‘in process’ label | PASS — risk visible |
| Q26 | Funding Unknown | Risk and action | PASS — risk visible |
| Q27 | Client budget missing | Action; no synthetic price; not No-Go | PASS — ACTION REQUIRED |
| Q28 | Budget amount present; basis missing | Commercial action; route preserved | PASS — action visible |
| Q29 | Class D shows major budget gap | Commercial review action | PASS — Major Gap |
| Q30 | Aggressive/Unrealistic/Review timeline | Visible risk; no silent pass | PASS — three variants |
| Q31 | Existing controlled Class D result | Advance primary route to PCS | PASS — PCS |
| Q32 | Stale Class D amount while availability = No | Ignore stale amount; cannot bypass to PCS | PASS — Class D remains |
| Q33 | No Design plus stale Class D amount | CSA remains primary route | PASS — CSA |
| Q34 | Standard client selects LOI; policy disabled | Route unavailable; G1 blocked | PASS — blocked |
| Q35 | Returning client selects LOI before Class D | Cannot shortcut Class D | PASS — blocked |
| Q36 | Returning client + Class D + bounded LOI | LOI available only with governance | PASS — eligible |
| Q37 | LOI missing caps/trigger/review/sign-off | G1 blocked | PASS — blocked |
| Q38 | Assigned route does not match eligible route | G1 blocked | PASS — blocked |
| Q39 | Commercial instrument not Executed | G1 blocked | PASS — blocked |
| Q40 | High score + fatal hard rule | Hard rule wins | PASS — NO-GO |
| F01 | Form status Complete; required fields blank | Effective status remains incomplete | PASS — blocked |
| F02 | All fields complete; approval pending | Cannot complete | PASS — incomplete |
| F03 | Agreement executed; signature pending | Cannot complete | PASS — incomplete |
| F04 | Conditional/Triggered applicability Pending | Gates until determination | PASS — incomplete |
| F05 | N/A selected; reason blank/whitespace | N/A cannot bypass | PASS — incomplete |
| F06 | N/A selected with objective reason | Non-applicability accepted | PASS — complete |
| F07 | Approval or signature Rejected | Hard blocked state | PASS — blocked |
| F08 | Attempt to delete a controlled form | Deletion control unavailable | PASS — protected |

07 / VERIFICATION

# Automated and manual QA evidence

| Verification layer | Result | Coverage |
| --- | --- | --- |
| Deterministic rules | 63/63 passed | Qualification hard rules, routing, LOI, score precedence, L1/L2/L3 structure, 52-form catalog, completion/N/A/signature/approval loopholes |
| Browser interaction | 9/9 passed | App load, exact lifecycle, all 52 forms opening, controlled-form regression, N/A, document metadata, client hard block, matrix, mobile |
| Responsive & accessibility | 7/7 passed | L1/L2/L3 at five widths; visible inputs/buttons named; duplicate IDs absent on Gate, form and matrix screens |
| Report screenshots | 5/5 passed | Deterministic capture of L1, L2, L3, hard blocker and source QA |
| Static quality | Passed | TypeScript, ESLint, git diff check |
| Production build | Passed | Next.js 16.3 optimized static build |
| Console/network | Passed | No browser console errors and no HTTP 4xx/5xx on clean load |

Dependency note npm audit reports two Moderate entries that are the same transitive chain: exceljs 4.4.0 → uuid 8.3.2. ExcelJS uses uuid v4 without the advisory's v3/v5/v6 buffer argument, so the current export path is not the affected call pattern. No forced downgrade was applied because npm's suggested fix would move ExcelJS to 3.4.0 and risks breaking exports. There are zero High or Critical findings.

08 / BUG & UI REVIEW

# Issues found and corrected

| Finding | Failure risk | Correction in current system |
| --- | --- | --- |
| L1 structure drift | G1 was not a distinct L1/L2 control and the commercial path could appear as a peer L1 phase. | Restored exact 13-node L1; Commercial Pathway lives under Pre-Construction; G1 is a distinct Gate. |
| Route bypass | Opportunity could connect directly to Commercial Pathway. | Canonical edge is Opportunity → G1 → Commercial Pathway; migration removes the bypass. |
| Authority-state mismatch | Partially Confirmed could be visually blocked but pass the underlying Gate decision. | Partially Confirmed is now a deterministic Hard Hold in both UI and rule engine. |
| ‘Confirmed’ without evidence | No name/role or approval path was required. | Final Authority Name, Role/Title and Approval Path are mandatory hard-control evidence. |
| Class D misuse | A price could be treated as a pre-G1 prerequisite or fabricated from defaults. | G1 only assigns route; storeys + GFA are mandatory; no amount/formula is invented. |
| Maturity shortcut | Permit/IFC maturity could be mistaken for modular compatibility. | Separate fields and Technical Review/No-Go rules block incompatible or unreviewed design. |
| Controlled-form gaps | The previous L3 model did not expose every indexed/source form consistently. | 52 unique catalog forms are seeded once and open from their linked L2 nodes. |
| Form completion bypass | Status could be set Complete while required fields, signature or approval were missing. | Effective progress derives from fields + status + signature + approval + task state. |
| N/A bypass | Conditional/triggered records could disappear without evidence. | Pending applicability gates; N/A requires an objective reason. |
| Controlled form deletion | A catalog record could be removed and silently reduce the control set. | Catalog forms and Gate controls cannot be deleted; Clear L3 removes custom items only. |
| Uncontrolled collaboration | The page automatically connected to a public relay. | Collaboration is Off/Local unless a user explicitly creates or opens a share link. |
| Auth-bypass request error | Local bypass mode still called a missing /api/auth/me endpoint. | Cloud controls skip that request in bypass mode; no failed response remains. |
| Missing favicon | Browser requested a non-existent icon. | A controlled app icon now eliminates the 404. |
| Unlabelled controls | 11 Gate 1 secondary inputs had visual labels but no programmatic accessible name. | All 11 were associated with labels/ARIA; deep L3 and matrix scans now pass. |
| Responsive density | Dense L2/L3 layouts risked document-level horizontal overflow. | L1/L2/L3 verified at 390, 768, 1024, 1440 and 1920 px without document overflow. |
| Source naming drift | SER/MALR/ODN/PCR names and DC/CD/SOW/PSO/WMA numbering could conflict. | Controlled titles corrected; source discrepancies remain visible as QA notes. |

08 / UI ACCEPTANCE

# Current UI acceptance result

| 5 verified viewport widths | 0 document overflows | 0 unnamed visible controls | 0 clean-load request errors |
| --- | --- | --- | --- |

L1 remains visually simple and includes a compact 13-step overview.

L2 makes G1 and the bounded Commercial Pathway visually explicit.

L3 exposes all documents, matrices, source notes and operational fields without changing L2 into a document dump.

The mobile layout uses internal scrolling where required but never causes document-level horizontal overflow.

Collaboration state is clearly labelled Off/Local until explicitly activated.

Controlled forms show immediate blocker text when values regress after completion.

09 / MANAGEMENT DECISIONS RETAINED

# Explicit TBDs were preserved—not guessed

These items are copied from the Master Requirements TBD list. They require JF/Management/legal/commercial approval before the working control becomes final policy.

| JF / Management TBD (source wording) | Current system treatment |
| --- | --- |
|  | Working G1–G5 names and approval rows are visible; final authority remains management-controlled. |
|  | G2 working conditions are present; exact contractual trigger is not declared final. |
|  | SA is mapped across Commercial/G2/Readiness as Conditional; legal hierarchy remains open. |
|  | Represented as an L2 hard-control topic; no invented payment threshold. |
|  | All maturities are tracked separately from compatibility; final trigger remains open. |
|  | CEC supports D/C/B/A evidence; no permanent B/A policy mapping is fabricated. |
|  | Current minimum objective controls are implemented; configurable policy can evolve after sign-off. |
|  | Current engine permits paid-route qualification with a visible budget action; final policy remains open. |
|  | G2 contains a working Class C-ready basis; exact minimum remains a management decision. |
|  | No formula/default is invented; tolerance is a configurable rule and CEC records assumptions. |
|  | PCS fee basis is document-controlled, not hard-coded. |
|  | No customer-specific amount or policy is encoded. |
|  | Working bounded logic and signatures exist; business-rule/signing policy stays configurable. |
|  | G3/PSO/MPS controls are present; absolute prerequisite/approver awaits sign-off. |
|  | Payment remains a release condition placeholder; no amount or milestone is fabricated. |
|  | G5/WMA/closeout track the basis and dates; contractual trigger remains project/policy controlled. |
|  | Current project identifier supports the workflow; final enterprise hierarchy remains separate work. |
|  | Lifecycle status supports future reporting; threshold/notification policy is not invented in this release. |
|  | Proof of concept remains local/web-ready; enterprise integration is intentionally outside this deliverable. |

10 / ACCEPTANCE CONCLUSION

# Ready for controlled review and project replay

Acceptance position All source-definable lifecycle, Gate 1, form-register, matrix and completion-control requirements in scope are implemented and verified. The remaining limitations are not hidden software defects: they are damaged/missing source artifacts, explicitly open management policies, and enterprise modules intentionally outside this lifecycle release.

## Recommended next controlled actions

JF/Management reviews and signs the 19 retained TBD decisions in Section 9.

Document Control replaces the 30 index-only records with approved bilingual source masters as those templates are formally issued.

The source owner repairs/re-exports Combined Forms.pdf pages 179–193 and resolves controlled numbering discrepancies.

Run one past-project replay and one live-project soft launch; capture real hold durations, role conflicts and missing evidence before broad rollout.

After policy sign-off, lock the final Gate authority, payment/release mapping, warranty triggers and enterprise ID/time-tracking integration.

## Definition of done achieved in this release

| Acceptance criterion | Result |
| --- | --- |
| Three layers connected | Yes — 13 L1 nodes link to 14 L2 nodes; every L3 record has a valid L2 home/touchpoint. |
| All forms in L3 | Yes — 52/52 controlled records, including supplemental SMO. |
| Matrices in L3 | Yes — 57-row Approval Matrix and 18-row Responsibility Matrix. |
| Non-compliant client blocking | Yes — authority, decision group, scale, fatal site, modular compatibility, route and engagement hard controls. |
| Form loophole blocking | Yes — fields, applicability, N/A evidence, signature, approval, task and deletion protections. |
| UI/bug review | Yes — responsive, accessible, clean-load and production-build checks passed. |
| No invented policy | Yes — all explicit source TBDs remain visible for authorized decision. |

End of controlled report.